## TMS_SLA Report
Application |  | Anna Darpan
Report Name |  | Ticket management System
Reporting Period |  | 01-07-2026 to 31-08-2026
Report Date: |  | 2026-02-09
SLA Status |  | SLA met
Ticket Summary
Total Ticket Raised | 6683
Resolved | 3778
Closed by Users | 1771
Open | 0
Assigned (In-Progress) | 216
On-Hold (Pending with Requestor) | 431
On-Hold (Pending with FCI) | 353
Change Request | 134

## SLA_System Availability
Application |  | Anna Darpan
Report Name |  | System Availability (Availability of all services/modules measured in terms of Uptime)
Reporting Period |  | 01-07-2026 to 31-08-2026
Report Date: |  | 2026-02-09
Total Calendar Hours |  | 1488
DR time |  | 126.52
Total Available Time |  | 100%
SLA Target |  | 99.5%
SLA Status |  | Within SLA
Month-wise Availability Summary
Month | Total Hours | Availability (%) | SLA Target | Status | Remarks
2026-07-01 | 744 | 100% | 99.5% | SLA MET | From 19th jul to 24th of jul sytem was in DR region hyderabad
2026-08-01 | 744 | 100% | 99.5% | SLA MET | -
Overall | 1488 | 100% | 99.5% | SLA MET | -
Note: Screenshot attached Separately Refer folder: SLA Reports -> SLA Screenshots -> System Availbility

## SLA_Monitoring
Application |  | Anna Darpan
Report Name |  | Monitoring system availbility and any part thereof (detection of non-availability)
Reporting Period |  | 01-07-2026 to 31-08-2026
Report Date: |  | 2026-02-09
System Non-Availability Instances |  | 0
SLA Target |  | Resolved within 15min.
SLA Status |  | SLA met
Downtime Incident Details
Date | Start Time | End Time | Duration (Minutes) | Reason | Status
- | - | - | - | - | Not applicable for July & August

## SLA_ResponseTime
Application |  | Anna Darpan
Report Name |  | Application response time – (This is the time taken from submission of any request by end user to response of the request to the end user)
Reporting Period |  | 01-07-2026 to 31-08-2026
Report Date: |  | 2026-02-09
SLA Target |  | ≤ 2.00 sec
SLA Status |  | SLA met
Monthly SLA Compliance Summary
Month | Environment | Average Response Time | SLA Target (Sec) | Status | Remark
2026-07-01 | DC | 1ms | ≤ 2.00 | SLA MET | Screenshot attached Separately
2026-08-01 | DC | 1ms | ≤ 2.00 | SLA MET
2026-07-01 | DR | 10ms | ≤ 2.00 | SLA MET
Note: Screenshot attached Separately Refer folder: SLA Reports -> SLA Screenshots -> Module Response and DR
Monitoring Location Wise Performance
Monitoring System | System Detail | Avg Response Time | Avg Target Response Time (Sec) | Status
User Request -1 | Asset-PROD | 162 ms | ≤ 2.00 | SLA MET
User Request -2 | Reports-PROD | 315 ms | ≤ 2.00 | SLA MET
User Request -3 | Labour-PROD | 51 ms | ≤ 2.00 | SLA MET
User Request -4 | Procurement-PROD | 76 ms | ≤ 2.00 | SLA MET
User Request -5 | Sales-PROD | 65 ms | ≤ 2.00 | SLA MET

## SLA_HomePage
Application |  | Anna Darpan
Report Name |  | Performance – Portal’s Homepage before or after login
Reporting Period |  | 01-07-2026 to 31-08-2026
Report Date: |  | 2026-02-09
SLA Target |  | ≤ 2.00 sec
SLA Status |  | SLA met
Monthly SLA Compliance Summary
Month | Environment | Average Response Time | SLA Target (Sec) | Status | Remark
2026-07-01 | DC | 10 ms | ≤ 2.00 | SLA MET | Screenshoty attacehd Separately
2026-08-01 | DC | 2 ms | ≤ 2.00 | SLA MET
2026-08-01 | DR | 10 ms | ≤ 2.00 | SLA MET
Note: Screenshot attached Separately Refer folder: SLA Reports -> SLA Screenshots -> Anna Darpan Home Page
Monitoring Location Wise Performance
Monitoring System | System Detail | Avg Response Time | Avg Target Response Time (Sec) | Status
User Request -1 | Asset-PROD | 162 ms | ≤ 2.00 | SLA MET
User Request -2 | Reports-PROD | 315 ms | ≤ 2.00 | SLA MET
User Request -3 | Labour-PROD | 51 ms | ≤ 2.00 | SLA MET
User Request -4 | Procurement-PROD | 76 ms | ≤ 2.00 | SLA MET
User Request -5 | Sales-PROD | 65 ms | ≤ 2.00 | SLA MET

## SLA_Recovery Time
Application |  | Anna Darpan
Report Name |  | Recovery Time from Disaster requiring switching to DR site
Reporting Period |  | 01-07-2026 to 31-08-2026
Report Date: |  | 2026-02-09
SLA Target |  | RPO ≤ 5 Minutes ¦ RTO ≤ 1 Hour
SLA Status |  | SLA Met (pdf separately attached)
SLA Compliance Summary
Drill/Incident Date | Type (Actual DR / Quarterly Drill) | DC Stop Date | DR Activation Date | RTO Achieved | RPO Achieved | Service Interruption | Data Loss | Switch Back to DC | Status
19-07-2026 | DR Drill | 19th July 2026 | 19th July 2026 | Yes | Yes | Nill | Nill | 24th July 2026 | SLA met
Note: mail copy and Document attached Separately Refer folder: SLA Reports -> Mail & Document
Switchover Details
Parameter | Target SLA | Achieved
Recovery Point Objective (RPO) | ≤ 5 Minutes | SLA met
Recovery Time Objective (RTO) | ≤ 1 Hour | < 30 min
Service Continuity During Switchover | No Interruption | -
Data Loss | Nil | -
Successful Operations from DR Site | Required | Successful

## SLA_delay in CR
Application | Anna Darpan
Report Name | Delay in Change Request delivery during the Operations & Maintenance phase
Reporting Period | 01-07-2026 to 31-08-2026
Report Date: | 2026-02-09
SLA Target | within 15 days from the planned timeline
SLA Status | SLA met
CR Delivery Compliance Summary
CR ID | CR Description | Document Submission | Committed Delivery Date | Delivery Date | FCI Approval Date | Status
CR_DISFM Data entry edit functionality_v0.1 | DISFM edit Functionality | 27th July 2026 | 31st August 2026 | 14th August 2026 | 04th August 2026 | SLA met
CR_Data_Migration_WINGS to AnnaDarpan_0.1 | Data Migration | 25th August 2026 | - | - | Pending
CR_State_Agency_updated_workflow_v0.2 | FCI taking from State Agency | 20th August 2026 | - | - | Pending
CR_Asset_PV_0.2 | Asset PV | 17th August 2026 | - | - | Pending
Extension Matrix | Extension Matrix | 25th May 2026 | - | - | Pending
SMART PDS - North East | SMART PDS - North East | 25th May 2026 | - | - | Pending

## SLA_MIS Reports
Application | Anna Darpan
Report Name | Response time for generation of BI/MIS reports
Reporting Period | 01-07-2026 to 31-08-2026
Report Date | 2026-02-09
SLA Target | Ad-hoc Reports: ≤ 30 Seconds Standard Reports: ≤ 10 Seconds
SLA Status | SLA met
SLA Compliance Summary
Report Type | SLA Target | Status
Ad-hoc Reports | ≤ 30 Sec | SLA met
Canned/Standard Reports | ≤ 10 Sec | SLA met
S No | Report Type | Scope | Report Name | Time | Avg | Status
1 | Ad-hoc Reports | HQ | AI Assitance (Total Active Depots) | 9 secs, 10 secs, 9 secs | 9 seconds | Under SLA
2 | Ad-hoc Reports | HQ | AI Assitance (List All Depots with other details) | 14 secs, 15 secs, 15 secs | 15 seconds | Under SLA
3 | Standard Report | HQ | OtherTransaction_admin | 1031ms, 1015ms, 939ms | 995 ms | Under SLA
4 | Standard Report | DO | ROReport_district | 1279ms, 1476ms, 1550ms | 1,435 ms | Under SLA
5 | Standard Report | DO | DSIReport_districtwise | 684ms, 842ms, 731ms | 752.3 ms | Under SLA
6 | Standard Report | DO | CropYearWiseCurrentStockReport_district | 1023ms, 1039ms | 1,031 ms | Under SLA
7 | Standard Report | Depot | DSRReport | 1299ms, 1043ms | 1,171 ms | Under SLA
8 | Standard Report | Depot | ShedWiseStorageLoss | 755ms | 755 ms | Under SLA
9 | Standard Report | Depot | ShedWiseStock | 951ms, 1092ms | 1,021.5 ms | Under SLA